## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a member, I should be able to search certifications so that I can find specific certificate(s) | 7 Points | Mahmoud Salah | Abd-El Rahman Ashraf | Moaz Ashraf
2 | As a member, I should be able to book a timing for an offline evaluation process so that I can undergo the evaluation in a proper time | 5 Points | Omar Handouk | Ahmed Nasr | Ahmed Zamarany
3 | As a member, I should be able to search tasks so that I can find tasks related to specific keywords | 7 Points | Ahmed Zamarany | Carol Guirguis | Zainab Sultan
4.1 | write unit tests for backend | 5 Points | Mahmoud Salah | Moaz Ashraf | Omar Handouk
4.2 | write unit tests for backend | 5 Points | Omar Handouk | Mahmoud Salah | Ahmed Zamarany
4.3 | write unit tests for backend | 5 Points | Ahmed Zamarany | Omar Handouk | Mahmoud Salah
4.4 | write unit tests for backend | 5 Points | Aya Mamdouh | Zainab Sultan | Omar Handouk
4.5 | write unit tests for backend | 5 Points | Moaz Ashraf | Aya Mamdouh | Carol Guirguis
4.6 | write unit tests for backend | 5 Points | Carol Guirguis | Ahmed Zamarany | Aya Mamdouh
4.7 | write unit tests for backend | 5 Points | Abd-El Rahman Ashraf | Ahmed Nasr | Moaz Ashraf
4.8 | write unit tests for backend | 5 Points | Ahmed Nasr | Abd-El Rahman Ashraf | Zainab Sultan
4.9 | write unit tests for backend | 5 Points | Zainab Sultan | Carol Guirguis | Abd-El Rahman Ashraf