## Sheet1
UNIQUE ID | USER STORY | ASSIGNEE | REVIEWER #1 | REVIEWER #2 | STORY POINTS
1 | As a registered user I should be able to login to LirtenHub by providing my information so that I can use the services | Carol | zamarany | mahmood | 3
2 | As an unregistered user, I should be able to sign up for lirtenhub by providing my basic information so that i can offer my services | Zainab | mahmood | zainab | 3
3 | As a registered user, I should be able to view membership information so that I can be aware of its expiry date | mahmood | Aya | Moaz | 5
4 | As a consultancy agency I should be able to view the current state of a task In progress so that I can monitor the progress | Aya | Omar | nasr | 3
5 | As a member, I should be able to apply for Certificates so that I increase my chances of getting tasks | Abdelrahman | moaz | nasr | 5
6 | As a member, I should be able to view a certification so that I may apply to it (CRUD) | Abdelrahman | Carol | Zainab | 4
7 | As a member, I should be able to search certifications so that I can find specific certificate(s) | Zamarany | abdelrahman | Aya | 4
8 | As a member, I should be able to view tasks so that I can apply to some of them | Omar Ehab | Moaz | zainab | 5
9 | As a member, I should be able to search tasks so that I can find tasks related to specific keywords | nasr | zamarany | carol | 3
10 | As a registered user I should be able to request to edit my basic information so that I can modify my profile | Moaz | mahmood | Aya | 4