## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Member Entity: | 8 in total for CRUD | Ahmed Nasr 40- 14043
1.1 | As a member I should be able to create my profile | 2 points | Ahmed Nasr | None | NO
1.2 | As a memberI should be able to view my profile | 2 points | Ahmed Nasr | None | NO
1.3 | As a member I should be able to edit my profile | 2 points | Ahmed Nasr | None | NO
1.4 | As a memberI should be to delete my profile | 2 points | Ahmed Nasr | None | NO
2 | Partner Entity: | 8 in total for CRUD | Ahmed El-Zamarany 40-11881
2.1 | As a partner I should be able to create my profile | 2 points | Ahmed El-Zamarany | None | NO
2.2 | As a partner I should be able to view my profile | 2 points | Ahmed El-Zamarany | None | NO
2.3 | As a partner I should be able to edit my profile | 2 points | Ahmed El-Zamarany | None | NO
2.4 | As a partner I should be able to delete my profile | 2 points | Ahmed El-Zamarany | None | NO
3 | Education Organisation: | 8 in total for CRUD + 5 for integration testing | Carol Guirguis 40- 1213 & Zainab Sultan 40- 2595
3.1 | As a Educational Organisation I should be able to create my profile | 2 points | Carol Guirguis | Zainab Sultan | YES
3.2 | As a Educational Organisation I should be able to view my profile | 2 points | Carol Guirguis | Zainab Sultan | YES
3.3 | As a Educational Organisation I should be able to edit my profile | 2 points | Zainab Sultan | Carol Guirguis | YES
3.4 | As a Educational Organisation I should be able to delete my profile | 2 points | Zainab Sultan | Carol Guirguis | YES
3.5 | Integration Testing for CRUD | 5 points | Carol Guirguis & Zainab Sultan | None | NO
4 | Co-working space entity: | 8 in total for CRUD | Mahmood Salah 40- 19135
4.1 | As a Co-working space I should be able to create my profile | 2 points | Mahmood Salah | None | NO
4.2 | As a Co-working space I should be able to view my profile | 2 points | Mahmood Salah | None | NO
4.3 | As a Co-working space I should be able to edit my profile | 2 points | Mahmood Salah | None | NO
4.4 | As a Co-working space I should be able to delete my profile | 2 points | Mahmood Salah | None | NO
5 | Consultancy Entity: | 8 in total for CRUD | Abdel-Rahman Ashraf 40- 17591
5.1 | As a Consultancy I should be able to create my profile | 2 points | Abdel-Rahman Ashraf | None | NO
5.2 | As a Consultancy I should be able to view my profile | 2 points | Abdel-Rahman Ashraf | None | NO
5.3 | As a Consultancy I should be able to edit my profile | 2 points | Abdel-Rahman Ashraf | None | NO
5.4 | As a Consultancy I should be able to delete my profile | 2 points | Abdel-Rahman Ashraf | None | NO
6 | Certification Entity: | 8 in total for CRUD + 5 for integration testing | Moaz Ashraf 40- 13278 & Aya Mamdoh 40- 19298
6.1 | As a Educational organisation I should be able to create a certificate | 2 points | Moaz Ashraf | Aya Mamdoh | YES
6.2 | As a Educational organisation I should be able to view my certificates | 2 points | Moaz Ashraf | Aya Mamdoh | YES
6.3 | As a Educational organisation I should be able to edit certificates | 2 points | Aya Mamdoh | Moaz Ashraf | YES
6.4 | As a Educational organisation I should be able to delete certificates | 2 points | Aya Mamdoh | Moaz Ashraf | YES
6.5 | Integration Testing for CRUD | 5 points | Moaz Ashraf & Aya Mamdoh | None | NO
7 | Task Entity: | 8 points for CRUD | Omar Handouk 40-3457
7.1 | As a partner I should be able to create tasks | 2 points | Omar Handouk | None | NO
7.2 | As a partner/member I should be able to view tasks | 2 points | Omar Handouk | None | NO
7.3 | As a partner I should be able to edit tasks | 2 points | Omar Handouk | None | NO
7.4 | As a partner I should be able to delete tasks | 2 points | Omar Handouk | None | NO