## Sheet1
# | User Story | Story Points | Assignee | Extra Notes
1 | Recommendation System | --- | --- | ---
1.1 | As a member, I should be able to receive certificate recommendations so that I can apply on some of them | 8 | Ahmed Al-Zamarany | 1. Implementing the Recommendation Algorithm, 2. Mirror the recommendation system to the Front End
1.2 | As a member, I should be able to view recommendations of tasks that matches my set of skills so that I can apply on some of them | 8 | Ahmed Al-Zamarany
2 | As a partner I should be able to view tasks that I applied for but the admin didn’t accepted yet | 5 | Zainab Sultan | Back End
3 | As a educational organisation I should be able to view certificates that I applied for but the admin didn’t accepted yet | 5 | Zainab Sultan | Back End
4 | As a partner I should be able to view tasks that I applied for but the admin didn’t accepted yet | 5 | Zainab Sultan | Front End
5 | As a educational organisation I should be able to view certificates that I applied for but the admin didn’t accepted yet | 3 | Zainab Sultan | Front End
6 | As a member I should be able to view certificats that I applied for but didn’t accepted yet | 3 | Zainab Sultan | Front End & Back End
7 | As a member I should be able to view tasks that I applied for but didn’t accepted yet | 8 | Aya Mamdoh | Front End & Back End
8 | As a consultuncy I should be able to view tasks that I applied for but didn’t accepted yet | 8 | Aya Mamdoh | Front End & Back End
9 | As educational organisation I should be able to accept a member for certificate | 8 | Carol Guirguis | Front End & Back End
10 | As a partner I should be able to choose a member for a task | 8 | Carol Guirguis | Front End
11 | As a educational organisation I should be able to create certificate | 21 | Moaz Ashraf | ---
12 | As a user I should be able to view all certificate that are available | 21 | Ahmed Nasr El-Deen | ---
13 | Notification System | --- | --- | ---
13.1 | As a member, I should be able to receive a notification with the details of the evaluation process so that I can prepare for it | 5 | Abd El-Rahman Ashraf | ---
13.2 | As a partner I should be able to receive a notification about the time and location of negotiation phase so that I can attend it | 5 | Abd El-Rahman Ashraf | ---
13.3 | As a consultancy agency I should be notified when I am chosen for a task so that I can start co-operating with the partner | 5 | Abd El-Rahman Ashraf | ---
13.4 | As a member, I should be able to get notified if accepted so that I can start working on the task | 5 | Mahmood Salah | ---
13.5 | As a member, I should be able to be invited to orientation if accepted in a task so that I can get a better understanding of the task | 5 | Mahmood Salah | ---
13.6 | As an registered user pending approval, I should be able to receive notification with location and time to sign contract and agreements so that I can start using the platform | 5 | Mahmood Salah | ---
14 | As a user I should be able to view all tasks that are available | 8 | Omar Handouk | Styling Migration From MDB to Material UI and Back End Integration
15 | As a partner I should be able to view my projects | 8 | Omar Handouk | Styling Migration From MDB to Material UI and Back End Integration
16 | As a partner I should be able to view Tasks for a specific project | 8 | Omar Handouk | Styling Migration From MDB to Material UI and Back End Integration
17 | Admin Dashboard | --- | --- | ---
17.1 | As an admin I should be able to approve requests | 5 | Mahmood Salah | Requests are (Registration - Tasks - Certificate Creation - ...etc)
17.2 | As an admin I should be able to overview stats for the website | 5 | Abd El-Rahman Ashraf | Stats for (Active Requests - Number of Users - Types of Tasks - Applied Evaluation)
17.3 | As an admin I should be able to (assign members/delete users/remove tasks/change status) | 5 | Omar Handouk | Overall control over every operation that can be done on DB Models (Maybe even ability to send JSON)