## Sheet1
# | User Story | Story Points | Assignee | Extra Notes
1 | As a user I should be able to view a specific task | 21 | Ahmed Nasr El-Deen | Task Page, includes task details
2 | As a user I should be able to view all tasks that are available | 8 | Omar Handouk | ---
3 | As a partner I should be able to view my projects | 8 | Omar Handouk | ---
4 | As a partner I should be able to view Tasks for a specific project | 8 | Omar Handouk | ---
5 | Profile Pages | --- | --- | ---
5.1 | As a consultancy I should have a profile page | 8 | Mahmood Salah | ---
5.2 | As an educational organisation I should have a profile page | 3 | Mahmood Salah | ---
5.3 | As a partner I should have a profile page | 3 | Mahmood Salah | ---
6 | As a user I should authorized to do specific actions related to my account type | 8 | Mahmood Salah | JWT Tokenization
7 | Applications | --- | --- | ---
7.1 | As a member I should be able to fill an application to apply for a task | 13 | Carol Guirguis | ---
7.2 | As a consultancy I should be able to fill an application to apply for a task | 5 | Carol Guirguis | ---
8 | Test: As a partner I should be able to choose a member for a task | 3 | Carol Guirguis | ---
9 | As a user I should be able to edit my profile | 8 | Moaz Ashraf | ---
10 | As a partner I should be able to create tasks | 8 | Moaz Ashraf | ---
11 | As a partner I should be able to view my tasks | 8 | Moaz Ashraf | ---
12 | Reviewing | --- | --- | ---
12.1 | As a member I should be able to review projects I am related with | 8 | Abd El-Rahman Ashraf | ---
12.2 | As a partner I should be able to review projects I am related with | 5 | Abd El-Rahman Ashraf | ---
13 | As a user I should be able to login | 5 | Abd El-Rahman Ashraf | ---
14 | Keyword Search | --- | --- | ---
14.1 | As a user I should be able to search using keywords for tasks | 5 | Ahmed Al-Zamarany | Back-End Route + Front End View
14.2 | As a user I should be able to search using keywords for certificates | 5 | Ahmed Al-Zamarany | Back-End Route + Front End View
14.3 | As a user I should be able to search using keywords for members | 5 | Ahmed Al-Zamarany | Back-End Route + Front End View
15 | Admin Approvals | --- | --- | ---
15.1 | As an admin I should be able to approve tasks | 13 | Ahmed Al-Zamarany | Back-End Route, Front-End View (admin dashboard sprint 6)
15.2 | As an admin I should be able to approve profile edits | 13 | Ahmed Al-Zamarany | Back-End Route, Front-End View (admin dashboard sprint 6)
16 | As a partner I should not be able to put a skill level more than 10 for a task | 5 | Zainab Sultan | Validation JOI in Backend
17 | As a partner I should be able to choose my accepted payment methods | 5 | Zainab Sultan | Enumeration In Task Schema
18 | As a user I should be able to sign-up | 8 | Zainab Sultan | ---
19 | As an admin I should be able to add new skills to the system | 5 | Aya Mamdoh | Make a new Schema called Skills, Keys used {Skill name} serves as Enum
20 | Test: As an admin I should be able to add Skills | 5 | Aya Mamdoh | ---
21 | As a user I should be able to view information about the website | 13 | Aya Mamdoh | About Page
22 | As a partner I should be able to negotiate with a member | 13 | Abd El-Rahman Ashraf/ Mahmoud Salah | Chat Feature
21 | As a user I should be able to view information about the website | 13 | Abd El-Rahman Ashraf/ Mahmoud Salah | Chat Feature